## Sheet1 (hidden)
PROGRAM OF WORKS
DepED-CY 2013 BEFF(Repair of Earthquake Damaged SB) -RegionVII-Bohol
School: | BUENAVISTA ELEMENTARY SCHOOL |  |  | Date:
Budget Allocation:
Region: | VIII |  |  | Estimated Government Expenses:
Division: | BOHOL |  |  | Approved Budget for Contract: |  |  | 1000000
Project Title: |  |  |  | Completion Period: |  | 45 calendar days | 90 Calendar Days
REPAIR/ REHABILITATION OF SCHOOL BUILDINGS |  |  |  | Minimum Required Manpower:
|  |  |  | CIVIL ENGINEER |  | CARPENTER | PAINTER
|  |  |  | FOREMAN |  | STEELMAN
MASON
Plan: |  |  |  | Minimum Required Equipment:
Location: |  | CARMEN, BOHOL |  | ONE BAGGER MIXER |  | WELDING MACHINE | HAND TOOLS
|  |  |  | CONCRETE VIBRATOR |  | BAR CUTTER
Item I.D. | Item Description |  | % of Total | Unit | Quantity | Total Cost | Remarks
I. DIRECT COST
| General Requirements |  |  | lot | 1 | 56100
Bldg. 1 - 3 CL BLSB BUILDING
2 | Concreting Works |  |  | cu m | 9.39 | 57395
3 | Rebar Works |  |  | kg | 197.0645 | 9356.4338
4 | Formworks |  |  | sq m | 126 | 27661.4
5 | Masonry Works |  |  | sq m | 56 | 47573.5
6 | Doors and Windows |  |  | set | 3 | 19500
8 | Roofing Works |  |  | lot | 1 | 144264.9
9 | Carpentry Works |  |  | sq m | 171 | 85046
13 | Painting Works |  |  | sq m | 294.34 | 36725
Bldg 2- 3 CL MARCOS TYPE BUILDING
2 | Concreting Works |  |  | cu m | 9.39 | 57395
3 | Rebar Works |  |  | kg | 197.0645 | 9278.4338
4 | Formworks |  |  | sq m | 126 | 27661.4
5 | Masonry Works |  |  | sq m | 56 | 47573.5
6 | Doors and Windows |  |  | set | 3 | 23400
8 | Roofing Works |  |  | lot | 1 | 144264.9
9 | Carpentry Works |  |  | sq m | 144 | 53885
13 | Painting Works |  |  | sq m | 267.34 | 31850
BLDG 3- 3 CL BUILDING
| Concreting Works |  |  | cu m | 14.79 | 89791
| Rebar Works |  |  | kg | 197.0645 | 9278.4338
| Formworks |  |  | sq m | 126 | 27661.4
| Masonry Works |  |  | sq m | 93 | 38954.5
| Doors and Windows |  |  | set | 9 | 46800
| Steel Works |  |  | lot | 1 | 329983.7299
| Roofing Works |  |  | lot | 1 | 144264.9
| Carpentry Works |  |  | sq m | 171 | 85046
| Painting Works |  |  | sq m | 656.28 | 73060
| Sub-Total |  |  |  |  | 1723770.4314
II. INDIRECT COST _____% of (I)
| Overhead Expenses (____%) |  |  | 1% |  | 17237.7043
| Contingencies (____%) |  |  | 1% |  | 17237.7043
| Miscellaneous (_____%) |  |  | 1% |  | 17237.7043
| Contractor's Profit (____%) |  |  | 10% |  | 172377.0431
| Sub-Total |  |  |  |  | 224090.1561
| III. TAX 12% of (I+II) |  |  | 12% |  | 233743.2705
| Sub-Total |  |  |  |  | 233743.2705
| IV. TOTAL CONSTRUCTION COST (I + II + III) |  |  |  |  | 2181603.858
Prepared:
MUANA CONSTRUCTION AND DEVELOPMENT CORP.
Contractor/Contractor Representative

## BOQ (hidden)
Contract ID | :
Project Name | :
Location | :
BILL OF QUANTITIES
Part No. |  |  | Part Discription:
Pay Item No | Description | Unit | Quantity | Unit Price (Pesos) |  | Amount (Pesos)
-1 | -2 | -3 | -4 | -5 |  | -6
1 | Earthworks
1.1 | Structural Excavation of Column Footing | cu.m. |  |  | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
1.2 | Backfilling and Compaction | cu.m. |  |  | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
2 | Concrete Works and Rebar works
2.1 | RC Column Footing | cu.m. |  |  | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
[5 empty] | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
2.11 | Reinforcing Steel for Column Footing | kgs |  |  | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
2.2 | RC Column (including replacement for Wooden Column) | cu.m |  |  | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
Sub Total Page 1 | [6 empty] | Php | #N/A
Contract ID | :
Project Name | :
Location | :
BILL OF QUANTITIES
Part No. |  |  | Part Discription:
Pay Item No | Description | Unit | Quantity | Unit Price (Pesos) |  | Amount (Pesos)
-1 | -2 | -3 | -4 | -5 |  | -6
2.21 | Reinforcing Steel for Columns | kgs. |  |  | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
2.3 | RC Roof Beam | cu.m. |  |  | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
2.31 | Reinforcing Steel for Roof Beams | kgs. |  |  | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
[5 empty] | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
[5 empty] | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
[5 empty] | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
Sub Total Page 1 | [6 empty] | Php | #N/A
Contract ID | :
Project Name | :
Location | :
BILL OF QUANTITIES
Part No. |  |  | Part Discription:
Pay Item No | Description | Unit | Quantity | Unit Price (Pesos) |  | Amount (Pesos)
-1 | -2 | -3 | -4 | -5 |  | -6
[5 empty] | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
[5 empty] | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
2 | Concrete Works and Rebar works
[5 empty] | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
[5 empty] | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
2.11 | Reinforcing Steel for Column Footing |  |  |  | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
2.2 | RC Column (including replacement for Wooden Column)
[5 empty] | In words: Pesos |  | In words: Pesos
[5 empty] | #N/A |  | #N/A
[5 empty] | In figures: Php |  | In figures: Php
[5 empty] | #N/A |  | #N/A
Sub Total Page 1 | [6 empty] | Php | #N/A

## 103 (hidden)
DETAILED ESTIMATE
PROJECT NAME |  | : | #REF!
LOCATION |  | : | #REF!
ITEM NO. |  | : | 103
DESCRIPTION |  | : | Structure Excavation
Quantity |  | : | 5
Output per man-hour |  | : | 0.25
Unit of Measurement |  | : | m³
[11 empty] | Area | = | 0.5
MANPOWER | Designation |  |  | No. of Person | No. of Days | Daily Rate | Amount
[11 empty] | Vol. | = | 5
[8 empty] | 1 | 3 | 380
| Unskilled |  |  | 2 | 2.5 | 250 | 1250 | 2 | 3 | 270 | 1620
| Total Man-days |  | 2.5 | [7 empty] | 1620 |  |  | 20
2.5
| Sub-Total for 1 | [5 empty] | 1250
EQUIPMENT | Name and Capacity |  |  | No. of Units | No. of days | Hourly Rate | Amount
| Sub-Total for 2 | [5 empty] | 0
| Total (1+2) | [5 empty] | 1250
| Output per hour = |  | 0.25 | m³
Unit Cost
MATERIALS | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount
3. Materials (Material cost was based on the prevailing market price submitted 2nd quarter 2011)
| Sub-Total for 3 | [5 empty] | 0
| Direct Cost | [5 empty] | 1250
0
| Unit Direct Cost | [5 empty] | 250

## 505 (hidden)
DETAILED ESTIMATE
PROJECT NAME |  | : | #REF!
LOCATION |  | : | #REF!
ITEM NO. |  | : | 505
DESCRIPTION |  | : | Grouted Riprap
Quantity |  | : | 11
Output per man-hour |  | : | 0.15
Unit of Measurement |  | : | m³ |  |  | Length | 10 | Meters
[9 empty] | Length | = | 10 | mtrs
MANPOWER | Designation |  |  | No. of Person | No. of Days | Daily Rate | Amount |  | Area | = | 1.1125 |  | Top | = | 0.6 |  | Toe hood | = | 0.1
[13 empty] | Bottom | = | 0.75
[9 empty] | Vol. | = | 11 |  | Height | = | 1.5
| Skilled |  |  | 1 | 10 | 380 | 3800
| Unskilled |  |  | 4 | 10 | 250 | 10000
| Total Man-days |  | 10
| Sub-Total for 1 | [5 empty] | 13800
EQUIPMENT | Name and Capacity |  |  | No. of Units | No. of days | Daily Rate | Amount
Example
[9 empty] | One Bagger Fuel Consumption Per Day | [5 empty] | 6 | L/day | 41 | per Liter
| One Bagger Mixer |  |  | 1 | 9 | 246 | 2214 |  |  | = | 246
| Sub-Total for 2 | [5 empty] | 2214
| Total (1+2) | [5 empty] | 16014
| Output per hour = |  | 0.15 | m³
Unit Cost
MATERIALS | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount
| 3. Materials | [9 empty] | Factor
[11 empty] | Class A | Class B | Class C | Class D
| Portland Cement |  |  | bags | 29 | 260 | 7540 |  | Cement |  | 2.574 | 2.448 | 2.232 |  | 1.944
| Sand |  |  | m3 | 2 | 1260 | 2520 |  | Sand |  | 0.143 | 0.135 | 0.124 |  | 0.108
| Boulders, 5% wastage factor |  |  | m3 | 11.55 | 1200 | 13860 |  | Boulders |  | 1.05 | 1.05 | 1.05 |  | 1.05 | With 5% Watage Factor
| PVC Pipe, 3" Weepholes |  |  | m. | 3 | 160 | 480
[9 empty] | Pipe |  | 0.3
| Sub-Total for 3 | [5 empty] | 24400
| Direct Cost | [5 empty] | 40414
0.95058
| Unit Cost Per Cu.m. | [5 empty] | 3674 |  |  |  | 0.049418

## 311 (hidden)
DETAILED ESTIMATE
PROJECT NAME |  | : | #REF!
LOCATION |  | : | #REF!
ITEM NO. |  | : | 311
DESCRIPTION |  | : | Concrete Pavement
Quantity |  | : | 0
Output per man-hour |  | : | 0.45
Unit of Measurement |  | : | m² |  |  | Length | 10 | Meters
[9 empty] | Length | = |  | mtrs
MANPOWER | Designation |  |  | No. of Person | No. of Days | Daily Rate | Amount |  | Area | = | 0 |  | Thk | =
[13 empty] | Length | = | 0
[9 empty] | Vol. | = | 0 |  | Width | =
| Skilled |  |  | 2 | 0 | 380 | 0
| Unskilled |  |  | 4 | 0 | 270 | 0
| Total Man-days |  | 0
| Sub-Total for 1 | [5 empty] | 0
EQUIPMENT | Name and Capacity |  |  | No. of Units | No. of days | Daily Rate | Amount
Example
[9 empty] | One Bagger Fuel Consumption Per Day | [5 empty] | 10 | L/day | 41 | per Liter
| One Bagger Mixer |  |  | 1 |  | 410 | 0 |  |  | = | 410
| Sub-Total for 2 | [5 empty] | 0
| Total (1+2) | [5 empty] | 0
| Output per hour = |  | 0.45 | m²
Unit Cost
MATERIALS | Name and Specification |  |  | Unit | Quantity | Unit Cost | Amount
Concrete
| 3. Materials | [9 empty] | Factor
[11 empty] | Class AA | Class A | Class B | Class C
| Portland Cement |  |  | bags | 0 | 270 | 0 |  | Cement |  | 12 | 9 | 7.5 |  | 6
| Sand |  |  | m3 | 0 | #N/A | #N/A |  | Sand |  | 0.5 | 0.5 | 0.5 |  | 0.5
| Gravel, 5% wastage factor |  |  | m3 | 0 | 1200 | 0 |  | Gravel |  | 1.05 | 1.05 | 1.05 |  | 1.05 | With 5% Watage Factor
[9 empty] | Proportion |  | 1 : 1/2 : 3 | 1 : 2 : 4 | 1 : 2½ : 5 | 1 : 3 : 6
| Sub-Total for 3 | [5 empty] | #N/A
| Direct Cost | [5 empty] | #N/A
Unit Cost Per Cu.m.

## Sheet2 (hidden)
Republic of the Philippines
DEPARTMENT OF TRANSPORTATION AND COMMUNICATION
CIVIL AVIATION AUTHORITY OF THE PHILIPPINES
Hilongos Airport, Hilongos, Leyte
PROGRAM OF WORKS
(1) | Date
(2) | Agency |  | CAAP
(3) | Region |  | VIII
(4) | City/Municipality |  | HILONGOS, LEYTE
(5) | Name/Location of Project | (7) | Source of Fund | (8) | Issued Obligated |  |  | (9) | Funding
REPAIR/RENOVATION OF AIRPORT TERMINAL AT HILONGOS AIRPORT |  |  |  |  | Authority |  |  |  | Warrant
(6) | Plan Set No.
(10) | Project Description |  |  | (11) | Number of Calendar Days
REPAIR/RENOVATION OF AIRPORT TERMINAL |  |  |  | Ninety (90) Calendar Days
(12) | Technical Personnel Required |  |  | (13) | Equipment to be Used
Engineer
Foreman
(14) Estimated Cost by Item of Work
(Materials, Equipment and Labor)
(14.1) |  |  | (14.2) | (14.3) |  | (14.4) | (14.5) | (14.6)
Scope of Work to be Done |  |  | % of Total | Unit |  | Quantity | Unit Price | Total
ITEM | [7 empty] | Amount
| #REF! |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| #REF! |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| #REF! |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| #REF! |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| #REF! |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| #REF! |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| #REF! |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| #REF! |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| #REF! |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| #REF! |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
TOTAL DIRECT COST |  |  | #REF! |  |  |  |  | #REF!
BREAKDOWN OF ESTIMATED EXPENDITURES | [6 empty] | AMOUNT | % TOTAL
I. ESTIMATED DIRECT COST
A. | DIRECT COST | [5 empty] | #REF! | #VALUE!
| 1. MATERIALS | [5 empty] | #REF! | #VALUE!
1.1 COST AT SOURCE
1.2 TRANSPORT EXPENSES
1.3 STORAGE COST
| 2. LABOR | [5 empty] | #REF! | #VALUE!
2.1 DIRECT LABOR
| 3. EQUIPMENT | [5 empty] | 0
2.1 RENTALS
4. MOBILIZATION/DEMOBILIZATION
B. | INDIRECT COST | [5 empty] | #VALUE! | #VALUE!
| 1. OCM | [5 empty] | #REF! | #VALUE!
1.1 OVERHEAD
1.2 CONTINGENCIES
1.3 MISCELLANEOUS
| 2. CONTRACTORS PROFIT | [5 empty] | #REF! | #VALUE!
| 3. V.A.T. & CONTRACTOR'S TAX | [5 empty] | #REF! | #VALUE!
SUB-TOTAL | [6 empty] | #VALUE! |  | #VALUE!
II. | ESTIMATED GOVERNMENT EXPENSES
1. ROW / SITE ACQUISITION
2. SOIL EXPLORATION
3. PROJECT MANAGEMENT
4. MATERIALS TO BE FURNISHED BY THE GOVERNMENT
SUB-TOTAL | [6 empty] | 0 |  | 0%
III | CONTINGENCY RESERVES
1. PHYSICAL
2. PRICE ESCALATION
SUB-TOTAL | [6 empty] | 0 |  | 0%
TOTA PROJECT ESTIMATED COST | [6 empty] | #VALUE! |  | #VALUE!
PREPARED BY: |  |  |  | FUNDS AVAILABLE:
| ALLAN A. MEODE | [5 empty] | MERCEDES G. CINCO
| Officer - in - Charge | [5 empty] | Actg. Area/Airport Accountant
APPROVED:
DANILO T. ABARETA
Area Manager, Area VIII

## BACK UP COMPT (hidden)
Approved Budget |  |  | 1000000 | [7 empty] | Direct Cost |  |  | 542081.54
| Labor Cost |  | 350000 | [5 empty] | 650000 |  | Indirect Cost |  | % of Direct cost
| Material Cost | [9 empty] | Overhead Expenses |  | 5% | 27104.077 | 27104.077
[11 empty] | Contingencies |  | 2% | 10841.6308 | 10841.6308
| Column | [9 empty] | Miscellaneous |  | 1% | 5420.8154 | 5420.8154
| Assumming the Concrete pedestal is enough to carry the weight | [9 empty] | Contractors Profit |  | 12% | 65049.7848 | 65049.7848 |  |  | Item | Cost
[8 empty] | Cost | [5 empty] | 108416.308 | 108416.308 |  |  | Cement | 270
| L | 0.25 |  | Vol. |  | Cement | 24 | 270 | 6480 |  | Tax |  | 12% | 55009.957 | 55009.957 |  |  | Sand | 1500
| W | 0.25 |  | 2.625 |  | Sand | 1.3125 | 1500 | 1968.75 | [8 empty] | Gravel | 1500
| H | 3.5 |  |  |  | Gravel | 2.625 | 1500 | 3937.5 |  |  |  |  | 705507.805 |  | 294492.195 |  | Rebars | 45
| N | 12 |  |  |  | Rebars | 550.76 | 45 | 24784.2 | [8 empty] | Tie wire | 70
[6 empty] | Tie wire | 6.5 | 70 | 455 | [8 empty] | CHB | 19
[5 empty] | Forms | Rough Lumber 2" x 2" | 268 | 40 | 10720 |  |  | Rebars (Column) | [5 empty] | Rough Lumber | 40
[6 empty] | Ordinary plywood | 9 | 360 | 3240 |  |  | 0.256 | [5 empty] | Ordinary Plywood | 360
[6 empty] | CWN Assorted | 3 | 75 | 225 |  |  | 0.48 | [5 empty] | CWN Nails | 75
[6 empty] | Scaffolds | 518 | 40 | 20720
[9 empty] | 72530.45 |  |  | 0.25 | Use 0.25m Spacing for the lateral Ties
Roof Beam
[8 empty] | Cost |  |  |  | 180 | No. of Lateral Ties
| Length | 66.5 |  | Vol. |  | Cement | 52.3687 | 270 | 14139.5625 |  |  | 0.8 | mtr ties
| T | 0.35 |  | 5.8187 |  | Sand | 2.9094 | 1500 | 4364.0625 |  |  | 7.5 | pcs in one 10mm x 6m long steel bar
| w | 0.25 |  |  |  | Gravel | 5.8187 | 1500 | 8728.125 |  |  | 26 | pcs 10mm x 6m long bars |  |  | 96.2 | kgs
Rebars
[6 empty] | Tie wire | [5 empty] | 48 | pcs 16mm x 6m long bars |  |  | 454.56 | kgs
[5 empty] | Forms | Rough Lumber 2" x 2" | [5 empty] | 24 | pcs 16mm x 6m long bars |  |  | 284.16 | kgs
[6 empty] | Ordinary plywood | [10 empty] | 550.76
[6 empty] | CWN Assorted | [5 empty] | Tie wire
[9 empty] | 27231.75 |  |  | 336
[12 empty] | 6.3396 | Say
| Masonry | [11 empty] | 6.5 | kgs
| Hollowblocks |  | "4 CHB
Additional Concrete Hollowblocks
| Area |  |  |  |  | 5% Wastage Factor | Cost |  |  |  | No. of CHB |  |  | Rebars
| A1 | 13.8 |  | CHB | 988 | 1038 | 19 |  | 19722 | Side | 172.5 |  |  | V | 168.302
| A2 | 13.8 |  | Cement | 65 |  | 270 |  | 17550 |  | 172.5 |  |  | H | 169.8822
| A3 | 5.1 |  | Sand | 3.114 |  | 1500 |  | 4671 |  | 63.75 |  |  |  | 338.1842
Office | A4 | 34.515 |  | Gravel | 4.671 |  | 1500 |  | 7006.5 | Office | 431.4375 |  |  |  | 56.364
cr | A5 | 10 |  | Rebars | 56 |  | 45 |  | 2520 | Cr | 125 |  |  |  | 56 | pcs.
|  | 1.8 |  | Ties | 2.5 |  | 70 |  | 175 |  | 22.5
|  | 79.015 | [6 empty] | 51644.5
Tie Wire
| Plastering | [12 empty] | 2.0544 | kgs
Considering all wall Surfaces including area with openings
| A1 | 176.194 |  |  |  | Cement | 103 | 270 | 27810
| A1 | 32.445 |  |  |  | Sand | 8.5766 | 1500 | 12864.84
CR | A3 | 5.775 | [6 empty] | 40674.84
|  | 214.414 | [10 empty] | 3.848 | 7.696
[13 empty] | 1.89 | 9.45
| Covering for holes of all decorative blocks | [11 empty] | 0.84 | 3.36
vol.
| 15.12 | 30.24 | 3.024 |  | cement | 30 | [7 empty] | 20.506
| 2.25 |  | 0.225 |  | sand | 3.249
3.249
Total
[9 empty] | 192081.54 |  |  |  | Mobilization/Temporary Structures, Utilities and Services/Demobilization / Standard Billboard / Material Testing
457918.46
[16 empty] | Conrete demolition = |  | 5 men/0.31cu.m./hr.
| Doors and Windows | [5 empty] | SET | unit cost
[7 empty] | 4 | 2500 | 10000 |  |  |  | Demolition & disposal of debris
| 0.9m x 2.10m Panel Doors | [5 empty] | 4 |  | 0
| 1.4m x 1.2m Sliding Window | [11 empty] | Safety and Health
Roof Framing
| Decorative Filler Concrete | [10 empty] | Wooden Truss
[12 empty] | Full Truss | 9 |  | 8'
[12 empty] | 2" x 6" | 4.1 | 13.448 | 2
[13 empty] | 4.1 | 13.448 | 2
[13 empty] | 1.7 | 5.576 | 1
[13 empty] | 2.55 | 8.364 | 3 | 16.728
[13 empty] | 2.55 | 8.364
[13 empty] | 1.2 | 3.936 | 1 | 7.872
| ROOF | [11 empty] | 1.2 | 3.936 |  |  |  | 72 | 648
| 111.8 |  | 17.2 | [9 empty] | 17.4 |  | 9
| 6 |  | 6 | [9 empty] | 57.072
| 4 |  | 4.3
| 4.3 |  | 27.5 | 55 | [7 empty] | 2" x 4" | 1.215 | 3.9852 | 1 | 7.9704
| 126.1 | 252.2 | [10 empty] | 1.215 | 3.9852
[13 empty] | 0.65 | 2.132 | 1 | 4.264
|  |  | 307.2 | LM | [8 empty] | 0.65 | 2.132 |  |  |  | 10.6667 | 96
2
[12 empty] | Half Truss 1 | 4
[12 empty] | 2" x 6" | 5.5 | 18.04 | 3
[13 empty] | 3.61 | 11.8408 | 2 |  |  | 40 | 160
5
[12 empty] | 2" x 4" | 0.7 | 2.296 | 1 | 7.872
[13 empty] | 1.7 | 5.576 |  |  |  | 5.3333 | 21.3333
1
[12 empty] | Half Truss 2 | 2
[12 empty] | 2" x 6" | 4.1 | 13.448 | 3 | 21.812
[13 empty] | 2.55 | 8.364 |  |  |  | 24 | 48
3
[12 empty] | 2" x 4" | 0.7 | 2.296 | 1 | 6.56
[13 empty] | 1.3 | 4.264 |  |  |  | 5.3333 | 10.6667
1
[12 empty] | 856 | bd.ft. 2'' x 6" x 8'
[12 empty] | 128 | bd ft. 2" x 4" x 8'
[12 empty] | Purlins | 2'' x 3''
[11 empty] | 2 sides | 21.55 | 70.684 | 8.8355 | 9
[12 empty] | 22.75 | 74.62 | 9.3275 | 10
[12 empty] | 23.95 | 78.556 | 9.8195 | 10
[12 empty] | 25.15 | 82.492 | 10.3115 | 11
[12 empty] | 26.35 | 86.428 | 10.8035 | 11
[12 empty] | 27.55 | 90.364 | 11.2955 | 12
[12 empty] | 28.25 | 92.66 | 11.5825 | 12
[15 empty] | 75 | 150
[12 empty] | 0.4 | 1.312
[12 empty] | 1.6 | 5.248 |  | 1
[12 empty] | 2.8 | 9.184
[12 empty] | 4 | 13.12 |  | 3
[12 empty] | 5.2 | 17.056 |  | 3
[12 empty] | 6.4 | 20.992 |  | 3
[12 empty] | 7.1 | 23.288 | 2.911 | 3
[15 empty] | 13 | 26
[12 empty] | x-bracing | 8 | 2'' x 3''
[12 empty] | 6.4 | 20.992 | 2.624 | 3 | 24
[16 empty] | 200 | 800
[12 empty] | 800 | bd.ft. 2" x 3'' x 8'

## DE (hidden)
Project Name | : | Proposed Construction of Graduate Studies Building Roof
Location | :
Owner | : | Southern Leyte State University
ITEM NO. | DESCRIPTION |  | UNIT | QTY | UNIT COST |  | TOTAL COST |  | GRAND TOTAL
[5 empty] | MATERIAL | LABOR | MATERIAL | LABOR

## Sheet3 (hidden)
Column Footing |  |  | Volume
|  |  |  | Reinforcing bars | [5 empty] | Tie Wire
F-1 | 2.1 |  | 3.087 | 16.8 | 67.2 | 12 | 4.8 | m excess |  | 64 | 51.2
2 | 2.1 |  |  | 33.6 | [5 empty] | 128
0.35
F-2 | 2.5 |  | 10.9375 | 25 | 250 | 42 | 2 | mexcess |  | 100 | 200
5 | 2.5 |  |  | 50 | [5 empty] | 500
0.35
CF-1` | 3.5 |  | 2.5725 | 31.5 | 59.5 | 10 |  |  |  | 135 | 54
1 | 2.1 |  |  | 31.5
| 0.35 |  |  |  |  | 64 | pcs |  |  |  | 305.2 | length
|  | Total | 16.6 |  |  | 947.2 | kgs |  |  |  | 6 | kgs
Footing Tie Beam
FTB-1 | 0.5 |  | 9.98
49.9 | 0.4
|  | Total | 9.98
Column
|  |  |  | Main Bars |  |  |  |  | Lateral Ties | [7 empty] | Tie Wire
C-1 | 0.35 |  | 5.6534 | [10 empty] | Outer
5 | 0.35 |  |  | 4.9 | 4.33 | 20 | 100 |  | 16 | 14 | 30 | 150 |  | 1.2 | 59 |  | 3528
| 9.23 |  |  | 12 | 8 | [8 empty] | 352.8 |  |  | 1411.2 | mtrs
[14 empty] | Inner |  |  | 27 | kgs
4 | 0.35 |  | 5.39 | 4.9 | 6.1 | 20 | 80 |  | 16 | 20 | 36 | 144 |  | 1.5 | 36
| 0.35 |  |  | 12 | 8 |  | 180 | pcs | 80 | 70 |  | 294 | ties | 216
| 11 | [5 empty] | 2664 | kgs | 64 | 80 |  |  |  | 0.8 | 20
|  |  | 11.05 | [5 empty] | 144 | 150 |  |  |  | 120
[15 empty] | 115 | pcs
[15 empty] | 425.5 | kgs
Beams
B-1 | 0.25 |  | 9.95
79.6 | 0.5
B-2 | 0.25 |  | 2.02
20.2 | 0.4
RB-1 | 0.2 |  | 2.0048
25.06 | 0.4
SB-1 | 0.2 |  | 0.4
5 | 0.4
14.38
Suspended Slab
S-1 | 0.1 |  | 10.15
2 | 5.075
10
10.15
Slab on Fill
| 0.1 |  | 5.075
5.075
10
5.075

## GS-ROOF (5)
SOUTHERN LEYTE STATE UNIVERSITY
Sogod, Southern Leyte
BILL OF MATERIALS
Project Name | : | Proposed Construction of Graduate School Building Roof Deck Shed
Location | : | SLSU-Sogod (Main Campus), Sogod, So. Leyte
Owner | : | Southern Leyte State University
ITEM NO. | DESCRIPTION |  | UNIT | QTY | UNIT COST | TOTAL COST
2 | CONCRETE WORKS |  | cu.m.
| Portland Cement |  | bag
| Washed Sand |  | cu.m.
| Gravel, 3/4 |  | cu.m.
Sub-Total
3 | REBAR WORKS |  | kg.
| 16mm ø x 6m Reinforcing Steel Bars |  | pc.
| 10mm ø x 6m Reinforcing Steel Bars |  | pc.
| #16 G.I Tie Wire |  | kg.
Sub-Total
4 | FORMWORKS/SCAFFOLDINGS |  | sq.m.
| Coco Lumber, 2" x 2" x 8' |  | pc.
| Ordinary Plywood,¼"x4'x8' |  | shts.
| Common Wire Nails, #1 1/2 |  | kg.
| Common Wire Nails, # 3 |  | kg.
| Common Wire Nails, # 4 |  | kg.
Sub-Total
6 | STEEL WORKS
| Cee Purlins, 2" x 4" x 1.2mmthk x 6m |  | lgth
| Angle Bar, 1" x1" x ¼" x 6m |  | lgth
| Angle Bar, 1½" x 1½" x ¼"thk x 6m |  | lgth
| Angle Bar, 2"x 2" x ¼"thk x 6m |  | lgth
| Plain Round Bar 10mmØ x 6m |  | lgth
| Plain Round Bar 12mmØ x 6m |  | lgth
| Turn Buckle 12 mmØ |  | pc
| Steel Plate 1.20m x 2.40m x 10mm |  | shts.
| Anchor Bolt with Nuts and Washer, 12mmØ x 50mm x 300mm |  | pc.
| Cut-off Blade, 335mm x 3mm x 25.4mm |  | pc.
| Primer, Gray |  | gal
| Welding Rod |  | kg.
Sub-Total
7 | ROOFING WORKS
| Pre-painted G.I. Roofing, Rib type, 1220 x 0.40mm (Oceanic Blue) |  | l.m.
| Ridge Roll, Pre-Painted, Ordinary, 0.915m x 2.440m x 0.4mm thk (Oceanic Blue) |  | pc.
| Pre-painted Metal Fascia, 250mm x 2440mm (White) |  | pc.
| Aluminum foil insulation (4' x 50m roll) |  | roll
| J-bolt, 6mm |  | pc.
| Blind Rivets |  | pc
| #16 G.I. Tie Wire |  | kg.
| Roof Sealant |  | ltr.
Sub-Total
10 | ELECTRICAL WORKS
| PVC Conduit Pipe, ½"Ø |  | pc
| PVC Elbow (long), ½"Ø |  | pc
| Utility Box |  | pc
| Cee Purlins, 2" x 4" x 1.2mmthk x 6m |  | lgth
| Angle Bar, 2"x 2" x ¼"thk x 6m |  | lgth
| G.I. Pipe, 1"Ø x 6m sch 40 |  | lgth
| Welding Rod |  | kg.
| #16 G.I.Tie Wire |  | kg.
Sub-Total
14 | PAINTING WORKS |  | sq.m.
| Paint Brush 4" |  | pc
| Roller Brush 7" |  | pc
| Sand Paper #100 |  | pc
| Masonry Putty |  | gal
| Latex, Flat |  | gal
| Latex, Semi Gloss |  | gal
| Tinting Color, raw sienna latex |  | qrt
Sub-Total
TOTAL MATERIAL COST
A. | DIRECT COST
| 1. | Material Cost |  |  |  | 0
| 2. | Labor Cost (35% of A.1) |  |  |  | 0
| 3 | Cutting & chipping of existing floor only for installation of columns including chipping of one portion of existing parapet wall, removal of guardrail at the upper roof deck and relocation of its access stair using the removed item for its landing.
Sub-Total
B. | INDIRECT COST
| 1 | Contingency Allow. (5% of A.1)
| 2 | VAT, Taxes, Misc. (7% of A.1-2 + B.1)
| 3 | Contractor's Profit (10% of A. 1-3)
Sub-Total
c. | ADMINISTRATIVE COST
| 1 | Supervisions Cost (Management Technical Inspectors Team)
Sub-Total
TOTAL PROJECT COST
Prepared by: |  |  |  | Noted by:
Recommending Approval: |  |  |  | Approved by:
Note on F36: RYAN: truss mem + allow
Note on F37: User: truss/beam+clip angle+allow
Note on F62: User: truss/beam+clip angle+allow

## Sheet4 (hidden)
FT-1 |  |  |  |  | STB-2
2 | main bar | 4 | 28 |  | 6 | main bar
1.5 | member | 2.5 | 17.5 |  | 4.5 | member
2 | main bar
1 | member |  |  |  | STB-1
6.5 |  |  |  |  | 24 | main
7 | pcs |  |  |  | 32 | member
Ht-1 |  |  | total | #VALUE! | member
3 | main bar | 12 | total | 69.5 | main
2 | member | 8
Ht-2
1.5 | member | 9
canope
4 | main bar | 8
2.5 | member | 5
| 69.3 |  |  |  | #REF!
5.35
4.35
3.35
7.05
| 89.4 | 357.6
sag rod\ |  |  |  | steel post
76 |  |  |  | 14
120 |  |  |  | 3.5 | 2.5
196 |  |  |  | 3.5 | 2.5
purlins
237 | 474 |  |  | column
57.25 | 114.5 |  |  | 20 | 3.8 | 6.84 | 6.84
| 588.5 | 98.0833 |  | 2 | 2 | 0.36 | 0.36
Ridge roll | [6 empty] | 7.2
17.2 |  |  |  | Forms
18 |  |  |  | 1.4 | 25.2 | sq.m. 5 col.
33.6 |  |  |  |  | 8.75 | pcs. Ply wood
68.8 | 30.7143 |  |  |  | 267.03 | bd.ft.
Scaffolds
67.68
302.4
168.48
538.56
RSb
4 | pcs. 12mm x 6
80 | pcs. 12mm x 6 main bars |  |  |  | 4 | 1.4
1.4
1.4
1.4
5.6